## Summary
Phase | Phase Name | Min Days | Max Days | Avg Days | Tasks Count
Phase 1 | Project Foundation & Setup | 6 | 8 | 7 | 4
Phase 2 | Core Domain Models & API Layer | 6 | 8 | 7 | 4
Phase 3 | Workflow Canvas & UI Components | 6 | 8 | 7 | 3
Phase 4 | Workflow Execution Engine | 6 | 10 | 8 | 3
Phase 5 | API Node Integration & HTTP Client | 4 | 6 | 5 | 4
Phase 6 | Code Execution Security | 4 | 6 | 5 | 2
Phase 7 | Data Viewing & Display | 4 | 4 | 4 | 2
Phase 8 | Authentication & Security | 4 | 6 | 5 | 3
Phase 9 | Advanced Features & Workflow Management | 6 | 8 | 7 | 4
Phase 10 | Performance & Optimization | 4 | 4 | 4 | 3
Phase 11 | Testing & Quality Assurance | 6 | 8 | 7 | 4
Phase 12 | Documentation & Deployment | 4 | 4 | 4 | 3
TOTAL |  | 60 | 80 | 70 | 39

## All Tasks
Phase | Task ID | Task Name | Estimated Time | Priority | Breakdown Items | Deliverables
Phase 1 | 1.1 | Frontend Project Setup | 2-2 days | High | N/A | • Angular + TypeScript project initialization • Tailwind CSS configuration • Project structure setup • Development environment configuration • Build and dev server setup
Phase 1 | 1.2 | Backend Project Setup | 2-2 days | High | N/A | • Spring Boot project initialization • Database configuration (PostgreSQL/MySQL) • Maven/Gradle dependency management • Application properties configuration • Basic project structure • Development environment setup
Phase 1 | 1.3 | Database Schema Design & Migration | 2-2 days | High | N/A | • Workflow entity design • Node entity design • Edge/Connection entity design • Execution history schema • User and authentication schema • Liquibase/Flyway migration setup • Entity relationships and constraints
Phase 1 | 1.4 | API Client & REST API Foundation | 2-2 days | High | N/A | • Frontend HTTP client setup (Angular HttpClient) • REST controller structure • DTOs (Data Transfer Objects) • Exception handling framework • API response standardization • CORS configuration • Basic validation
Phase 2 | 5.1 | Project Setup & Configuration | 2-2 days | High | N/A | • Spring Boot project initialization • Database configuration (PostgreSQL/MySQL) • Maven/Gradle dependency management • Application properties configuration • Basic project structure
Phase 2 | 5.2 | Database Schema Design & Migration | 2-2 days | High | N/A | • Workflow entity design • Node entity design • Edge/Connection entity design • Execution history schema • Liquibase/Flyway migration setup • Entity relationships and constraints
Phase 2 | 2.1 | Core Domain Models & Repositories | 2-2 days | High | N/A | • JPA entities for Workflow, Node, Edge, User • Repository interfaces (Spring Data JPA) • Entity relationships mapping • Service layer architecture • Data validation annotations
Phase 2 | 2.2 | Workflow Management API & Frontend Integration | 4-6 days | High | • Backend: Workflow CRUD endpoints (2-2 days) • Backend: Node management endpoints (2-2 days) • Backend: Edge/Connection endpoints (2-2 days) • Frontend: Angular service layer (2-2 days) • Frontend: Workflow API integration (2-2 days) • Integration testing and debugging (2-2 days) | • Complete workflow CRUD API • Frontend API integration • Workflow persistence in database • Real-time sync between frontend and backend
Phase 3 | 3.1 | Workflow Canvas UI | 2-4 days | High | • Workflow canvas component setup and configuration (2-2 days) • Node palette component with API integration (2-2 days) • Node rendering and styling (2-2 days) • Drag and drop functionality (2-2 days) • Canvas controls and zoom (2-2 days) | • Interactive workflow canvas • Node palette with backend sync • Smooth drag and drop experience
Phase 3 | 3.2 | Node Types UI Implementation | 2-4 days | High | • Node component architecture (2 days) • All 5 node types visual design (2-2 days) • Node selection and interaction (2-2 days) • Connection handles and edge creation (2-2 days) • Backend sync for node changes (2-2 days) | • All node types with visual representation • Node connection functionality • Real-time backend synchronization
Phase 3 | 3.3 | Node Editor UI (3-Column Layout) | 2-4 days | High | • Right-click context menu (2-2 days) • 3-column layout implementation (2-2 days) • Previous node response panel (2-2 days) • Node configuration panel (2-2 days) • Current node response panel (2-2 days) • Backend data integration (2-2 days) | • N8N-style node editor • Integrated data display panels • Seamless backend integration
Phase 4 | 4.1 | Backend Execution Engine | 4-4 days | High | • Execution service architecture (2-2 days) • Topological sorting implementation (2-2 days) • Execution context management (2-2 days) • Node execution orchestration (2-2 days) • Execution state tracking and persistence (2-2 days) | • Workflow execution service • Execution history storage • Result persistence
Phase 4 | 4.2 | Node Runners Implementation (Backend) | 2-4 days | High | • Node runner framework (2-2 days) • Trigger node runner (2-2 days) • API node runner with HTTP client (2-2 days) • Condition node runner (2-2 days) • Code node runner (sandbox) (2-2 days) • Do Nothing node runner (2 days) | • All node types executable • Secure code execution • HTTP client integration
Phase 4 | 4.3 | Execution API & Frontend Integration | 2-2 days | High | • Execution endpoints (2-2 days) • Single node execution endpoint (2-2 days) • Execution status API (2-2 days) • Frontend Angular service (2-2 days) • Real-time execution updates (2-2 days) | • Execute workflow API • Execute single node API • Frontend execution integration • Execution status tracking
Phase 5 | 5.1 | HTTP Client Service (Backend) | 2-2 days | High | N/A | • REST client implementation (RestTemplate/WebClient) • Request/response handling • Timeout configuration • SSL/TLS support • Error handling
Phase 5 | 5.2 | API Node UI & Configuration | 2-2 days | High | • API node configuration form (2-2 days) • Authentication configuration UI (2-2 days) • Request preview/validation (2-2 days) • Backend integration (2-2 days) | • Complete API node configuration UI • Authentication UI support • Request validation
Phase 5 | 5.3 | API Authentication Support | 2-2 days | High | N/A | • API key authentication • Bearer token support • OAuth 2.0 integration (basic) • Basic authentication • Custom header injection
Phase 5 | 5.4 | Response Caching & Rate Limiting | 2-2 days | Medium | N/A | • Cache implementation (Redis/EhCache) • Rate limiting per API endpoint • Request throttling
Phase 6 | 6.1 | Sandboxed Code Execution (Backend) | 4-4 days | High (Security Critical) | N/A | • Code execution sandbox implementation • Security policy enforcement • Resource limits (memory, CPU, time) • Isolated execution environment • Security audit logging
Phase 6 | 6.2 | Code Node UI & Integration | 2-2 days | High | • Code editor integration (Monaco/CodeMirror) (2-2 days) • Syntax highlighting (2 days) • Code node configuration UI (2-2 days) • Backend execution integration (2-2 days) | • Rich code editing experience • Secure code execution • Execution feedback UI
Phase 7 | 7.1 | Data Viewer Components (Schema, JSON, Table) | 2-2 days | High | • Schema generation service (2-2 days) • Table conversion logic (2-2 days) • Tab component integration (Angular Material/CDK) (2-2 days) • Data formatting and display (2-2 days) | • Schema view implementation • JSON view with formatting • Table view with data conversion
Phase 7 | 7.2 | Execution Results Display | 2-2 days | High | • Previous node response component (2-2 days) • Current node response component (2-2 days) • Backend data integration (2-2 days) • Real-time updates (2-2 days) | • Complete result display UI • Backend data integration • Real-time execution feedback
Phase 8 | 8.1 | Backend Authentication System | 2-4 days | High | N/A | • JWT token-based authentication • User registration/login endpoints • Password encryption • Token refresh mechanism • User management service
Phase 8 | 8.2 | Frontend Authentication UI | 2-2 days | High | • Login page component (2-2 days) • Registration page component (2-2 days) • Authentication service integration (2-2 days) • Route guards implementation (2-2 days) | • Complete authentication UI • Token management • Session handling
Phase 8 | 8.3 | Authorization & Permissions | 2-2 days | High | N/A | • Role-based access control (RBAC) • Workflow ownership • Permission management • Access control on API endpoints • Frontend permission checks
Phase 9 | 9.1 | Workflow Versioning | 2-2 days | Medium | • Backend versioning system (2-2 days) • Version UI and controls (2-2 days) • Rollback functionality (2-2 days) | • Version tracking system • Version comparison UI • Rollback capability
Phase 9 | 9.2 | Workflow Import/Export | 2-2 days | Medium | • Backend export/import API (2-2 days) • Frontend import/export UI (2-2 days) | • Export workflow to JSON/YAML • Import workflow from files • Validation and error handling
Phase 9 | 9.3 | Workflow Templates | 2-2 days | Low | • Backend template system (2-2 days) • Template library UI (2-2 days) | • Template storage system • Template selection UI • Template instantiation
Phase 9 | 9.4 | Scheduled Workflow Execution | 2-4 days | Medium | • Backend scheduler (Quartz) (2-2 days) • Schedule management API (2-2 days) • Schedule UI and configuration (2-2 days) | • Cron-based scheduling • Schedule management UI • Job monitoring
Phase 10 | 10.1 | Database Optimization | 2-2 days | Medium | N/A | • Database indexing strategy • Query optimization • Connection pooling configuration • Caching frequently accessed data
Phase 10 | 10.2 | Async Processing & Frontend Optimization | 2-2 days | Medium | • Backend async execution (2-2 days) • Frontend optimization (virtual scrolling, lazy loading) (2-2 days) | • Async workflow execution • Background job processing • Optimized UI for large workflows • Job status polling
Phase 10 | 10.3 | Caching Strategy | 2-2 days | Medium | N/A | • Redis cache integration • Cache warming strategies • Distributed caching • Cache invalidation
Phase 11 | 11.1 | Backend Unit Testing | 2-4 days | High | N/A | • Service layer unit tests • Repository layer tests • Controller unit tests • Utility function tests • Test coverage > 80%
Phase 11 | 11.2 | Frontend Unit Testing | 2-2 days | High | N/A | • Component unit tests (Jasmine/Karma) • Service and utility tests • State management tests (NgRx/RxJS) • UI interaction tests
Phase 11 | 11.3 | Integration Testing | 2-2 days | High | N/A | • API integration tests • Frontend-backend integration tests • End-to-end workflow tests • Test data management
Phase 11 | 11.4 | E2E Testing & Security Testing | 2 days | High | • E2E test setup (Playwright/Cypress) (2 days) • Critical user flow tests (2 days) • Security testing (2 days) | • E2E test suite • Security audit • OWASP compliance check
Phase 12 | 12.1 | API Documentation | 2-2 days | Medium | N/A | • OpenAPI/Swagger documentation • API endpoint documentation • Request/response examples • Authentication guide
Phase 12 | 12.2 | Deployment Setup | 2-2 days | High | N/A | • Docker containerization • Docker Compose for local development • Production deployment scripts • Environment configuration
Phase 12 | 12.3 | CI/CD Pipeline | 2-2 days | Medium | N/A | • GitHub Actions/Jenkins setup • Automated testing in pipeline • Automated deployment • Build and release process

## Phase 1
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
1.1 | Frontend Project Setup | 2-2 days | High | N/A | • Angular + TypeScript project initialization • Tailwind CSS configuration • Project structure setup • Development environment configuration • Build and dev server setup
1.2 | Backend Project Setup | 2-2 days | High | N/A | • Spring Boot project initialization • Database configuration (PostgreSQL/MySQL) • Maven/Gradle dependency management • Application properties configuration • Basic project structure • Development environment setup
1.3 | Database Schema Design & Migration | 2-2 days | High | N/A | • Workflow entity design • Node entity design • Edge/Connection entity design • Execution history schema • User and authentication schema • Liquibase/Flyway migration setup • Entity relationships and constraints
1.4 | API Client & REST API Foundation | 2-2 days | High | N/A | • Frontend HTTP client setup (Angular HttpClient) • REST controller structure • DTOs (Data Transfer Objects) • Exception handling framework • API response standardization • CORS configuration • Basic validation

## Phase 2
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
5.1 | Project Setup & Configuration | 2-2 days | High | N/A | • Spring Boot project initialization • Database configuration (PostgreSQL/MySQL) • Maven/Gradle dependency management • Application properties configuration • Basic project structure
5.2 | Database Schema Design & Migration | 2-2 days | High | N/A | • Workflow entity design • Node entity design • Edge/Connection entity design • Execution history schema • Liquibase/Flyway migration setup • Entity relationships and constraints
2.1 | Core Domain Models & Repositories | 2-2 days | High | N/A | • JPA entities for Workflow, Node, Edge, User • Repository interfaces (Spring Data JPA) • Entity relationships mapping • Service layer architecture • Data validation annotations
2.2 | Workflow Management API & Frontend Integration | 4-6 days | High | • Backend: Workflow CRUD endpoints (2-2 days) • Backend: Node management endpoints (2-2 days) • Backend: Edge/Connection endpoints (2-2 days) • Frontend: Angular service layer (2-2 days) • Frontend: Workflow API integration (2-2 days) • Integration testing and debugging (2-2 days) | • Complete workflow CRUD API • Frontend API integration • Workflow persistence in database • Real-time sync between frontend and backend

## Phase 3
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
3.1 | Workflow Canvas UI | 2-4 days | High | • Workflow canvas component setup and configuration (2-2 days) • Node palette component with API integration (2-2 days) • Node rendering and styling (2-2 days) • Drag and drop functionality (2-2 days) • Canvas controls and zoom (2-2 days) | • Interactive workflow canvas • Node palette with backend sync • Smooth drag and drop experience
3.2 | Node Types UI Implementation | 2-4 days | High | • Node component architecture (2 days) • All 5 node types visual design (2-2 days) • Node selection and interaction (2-2 days) • Connection handles and edge creation (2-2 days) • Backend sync for node changes (2-2 days) | • All node types with visual representation • Node connection functionality • Real-time backend synchronization
3.3 | Node Editor UI (3-Column Layout) | 2-4 days | High | • Right-click context menu (2-2 days) • 3-column layout implementation (2-2 days) • Previous node response panel (2-2 days) • Node configuration panel (2-2 days) • Current node response panel (2-2 days) • Backend data integration (2-2 days) | • N8N-style node editor • Integrated data display panels • Seamless backend integration

## Phase 4
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
4.1 | Backend Execution Engine | 4-4 days | High | • Execution service architecture (2-2 days) • Topological sorting implementation (2-2 days) • Execution context management (2-2 days) • Node execution orchestration (2-2 days) • Execution state tracking and persistence (2-2 days) | • Workflow execution service • Execution history storage • Result persistence
4.2 | Node Runners Implementation (Backend) | 2-4 days | High | • Node runner framework (2-2 days) • Trigger node runner (2-2 days) • API node runner with HTTP client (2-2 days) • Condition node runner (2-2 days) • Code node runner (sandbox) (2-2 days) • Do Nothing node runner (2 days) | • All node types executable • Secure code execution • HTTP client integration
4.3 | Execution API & Frontend Integration | 2-2 days | High | • Execution endpoints (2-2 days) • Single node execution endpoint (2-2 days) • Execution status API (2-2 days) • Frontend Angular service (2-2 days) • Real-time execution updates (2-2 days) | • Execute workflow API • Execute single node API • Frontend execution integration • Execution status tracking

## Phase 5
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
5.1 | HTTP Client Service (Backend) | 2-2 days | High | N/A | • REST client implementation (RestTemplate/WebClient) • Request/response handling • Timeout configuration • SSL/TLS support • Error handling
5.2 | API Node UI & Configuration | 2-2 days | High | • API node configuration form (2-2 days) • Authentication configuration UI (2-2 days) • Request preview/validation (2-2 days) • Backend integration (2-2 days) | • Complete API node configuration UI • Authentication UI support • Request validation
5.3 | API Authentication Support | 2-2 days | High | N/A | • API key authentication • Bearer token support • OAuth 2.0 integration (basic) • Basic authentication • Custom header injection
5.4 | Response Caching & Rate Limiting | 2-2 days | Medium | N/A | • Cache implementation (Redis/EhCache) • Rate limiting per API endpoint • Request throttling

## Phase 6
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
6.1 | Sandboxed Code Execution (Backend) | 4-4 days | High (Security Critical) | N/A | • Code execution sandbox implementation • Security policy enforcement • Resource limits (memory, CPU, time) • Isolated execution environment • Security audit logging
6.2 | Code Node UI & Integration | 2-2 days | High | • Code editor integration (Monaco/CodeMirror) (2-2 days) • Syntax highlighting (2 days) • Code node configuration UI (2-2 days) • Backend execution integration (2-2 days) | • Rich code editing experience • Secure code execution • Execution feedback UI

## Phase 7
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
7.1 | Data Viewer Components (Schema, JSON, Table) | 2-2 days | High | • Schema generation service (2-2 days) • Table conversion logic (2-2 days) • Tab component integration (Angular Material/CDK) (2-2 days) • Data formatting and display (2-2 days) | • Schema view implementation • JSON view with formatting • Table view with data conversion
7.2 | Execution Results Display | 2-2 days | High | • Previous node response component (2-2 days) • Current node response component (2-2 days) • Backend data integration (2-2 days) • Real-time updates (2-2 days) | • Complete result display UI • Backend data integration • Real-time execution feedback

## Phase 8
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
8.1 | Backend Authentication System | 2-4 days | High | N/A | • JWT token-based authentication • User registration/login endpoints • Password encryption • Token refresh mechanism • User management service
8.2 | Frontend Authentication UI | 2-2 days | High | • Login page component (2-2 days) • Registration page component (2-2 days) • Authentication service integration (2-2 days) • Route guards implementation (2-2 days) | • Complete authentication UI • Token management • Session handling
8.3 | Authorization & Permissions | 2-2 days | High | N/A | • Role-based access control (RBAC) • Workflow ownership • Permission management • Access control on API endpoints • Frontend permission checks

## Phase 9
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
9.1 | Workflow Versioning | 2-2 days | Medium | • Backend versioning system (2-2 days) • Version UI and controls (2-2 days) • Rollback functionality (2-2 days) | • Version tracking system • Version comparison UI • Rollback capability
9.2 | Workflow Import/Export | 2-2 days | Medium | • Backend export/import API (2-2 days) • Frontend import/export UI (2-2 days) | • Export workflow to JSON/YAML • Import workflow from files • Validation and error handling
9.3 | Workflow Templates | 2-2 days | Low | • Backend template system (2-2 days) • Template library UI (2-2 days) | • Template storage system • Template selection UI • Template instantiation
9.4 | Scheduled Workflow Execution | 2-4 days | Medium | • Backend scheduler (Quartz) (2-2 days) • Schedule management API (2-2 days) • Schedule UI and configuration (2-2 days) | • Cron-based scheduling • Schedule management UI • Job monitoring

## Phase 10
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
10.1 | Database Optimization | 2-2 days | Medium | N/A | • Database indexing strategy • Query optimization • Connection pooling configuration • Caching frequently accessed data
10.2 | Async Processing & Frontend Optimization | 2-2 days | Medium | • Backend async execution (2-2 days) • Frontend optimization (virtual scrolling, lazy loading) (2-2 days) | • Async workflow execution • Background job processing • Optimized UI for large workflows • Job status polling
10.3 | Caching Strategy | 2-2 days | Medium | N/A | • Redis cache integration • Cache warming strategies • Distributed caching • Cache invalidation

## Phase 11
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
11.1 | Backend Unit Testing | 2-4 days | High | N/A | • Service layer unit tests • Repository layer tests • Controller unit tests • Utility function tests • Test coverage > 80%
11.2 | Frontend Unit Testing | 2-2 days | High | N/A | • Component unit tests (Jasmine/Karma) • Service and utility tests • State management tests (NgRx/RxJS) • UI interaction tests
11.3 | Integration Testing | 2-2 days | High | N/A | • API integration tests • Frontend-backend integration tests • End-to-end workflow tests • Test data management
11.4 | E2E Testing & Security Testing | 2 days | High | • E2E test setup (Playwright/Cypress) (2 days) • Critical user flow tests (2 days) • Security testing (2 days) | • E2E test suite • Security audit • OWASP compliance check

## Phase 12
Task ID | Task Name | Estimated Time | Priority | Breakdown | Deliverables
12.1 | API Documentation | 2-2 days | Medium | N/A | • OpenAPI/Swagger documentation • API endpoint documentation • Request/response examples • Authentication guide
12.2 | Deployment Setup | 2-2 days | High | N/A | • Docker containerization • Docker Compose for local development • Production deployment scripts • Environment configuration
12.3 | CI/CD Pipeline | 2-2 days | Medium | N/A | • GitHub Actions/Jenkins setup • Automated testing in pipeline • Automated deployment • Build and release process